## Project Budget
Project Budget for Synergy in 1 year
Project Name: | Synergy
Department: | Game Development
Supervisor Name: | Dave Meyer
|  |  |  | Labor |  | Computers | [7 empty] | BALANCE
|  |  | Planned Hours | Actual Hours | $/HR | UNITS | $/UNITS | Travel | Other Equipment | Fixed | Misc. | BUDGETED | ACTUAL | UNDER/OVER
WBS | Project Tasks | Assigned To: | [9 empty] | 145000 | 131800 | 13200
1 | Programming | /// | 1500 | 1440 | 35 | 1 | 1000 | 0 |  | 400 |  | 55000 | 51800 | 3200 | (www.payscale.com, 2022d)
2 | Level Designing | /// | 720 | 640 | 32 | 1 | 1000 | 0 |  | 100 |  | 24000 | 21580 | 2420 | (www.payscale.com, 2023b)
3 | Producing the story / setting | Dave Meyer | 400 | 450 | 0 | 0 | 2000 | 0 |  | 10000 |  | 15000 | 10000 | 5000
4 | Sound FX | /// | 100 | 80 | 34 | 1 | 500 | 0 |  | 100 |  | 5000 | 3320 | 1680 | (www.payscale.com, 2022c)
5 | Animator | /// | 450 | 420 | 30 | 1 | 1000 | 0 |  | 100 |  | 15000 | 13700 | 1300 | (Payscale.com, 2022)
6 | Music | /// | 200 | 180 | 25 | 1 | 500 | 0 |  | 100 |  | 6000 | 5100 | 900 | (www.payscale.com, 2022b)
7 | Business Managing | /// | 480 | 480 | 30 | 1 | 200 | 0 |  | 200 |  | 16000 | 14800 | 1200 | (www.payscale.com, 2023a)
8 | Legal | /// | 20 | 20 | 40 | 0 | [5 empty] | 2000 | 800 | 1200
9 | Game testing | /// | 200 | 180 | 15 | 8 | 500 |  |  |  |  | 7000 | 6700 | 300 | (www.payscale.com, 2022a)
10 | Marketing | /// | [7 empty] | 4000 |  | 5000 | 4000 | 1000
| SUBTOTAL |  |  |  | 108600 |  | 8200 | 0 | 0 | 15000 | 0 | 150000 | 131800 | 18200
Extra for in-office | Project Tasks | Assigned To: | [10 empty] | 52725 | 184525
For 112m² | Rent | /// | [7 empty] | 30000 |  |  | 30000 | -30000 | (Walls, 2022a)
| Office furniture | /// | [7 empty] | 14460 |  |  | 14460 | -14460 | (Sullivan, 2018)
| Office Maintainance | /// | [7 empty] | 2240 |  |  | 2240 | -2240 | (Lengthorn, n.d.)
| Cost of Utilities | /// | [7 empty] | 6025 |  |  | 6025 | -6025 | (Walls, 2022b)
Lengthorn, P. (n.d.). The cost of building maintenance. [online] www.consultengsurvivor.com. Available at: https://www.consultengsurvivor.com/the-cost-of-building-maintenance [Accessed 22 Jan. 2023].
Payscale.com. (2022). Animator, 3D. [online] Available at: https://www.payscale.com/research/DE/Job=Animator%2C_3D/Salary [Accessed 21 Jan. 2023].
Sullivan, A. (2018). Furniture Budget Pricing Matrix for Commercial Clients in San Francisco. [online] The Space Place. Available at: https://thespaceplace.net/furniture-budget-pricing-matrix/ [Accessed 22 Jan. 2023].
Walls, P. (2022a). How Much Does It Cost to Rent Office Space For My Business? - Starter Story. [online] www.starterstory.com. Available at: https://www.starterstory.com/office-space-costs [Accessed 22 Jan. 2023].
Walls, P. (2022b). What Is The Average Utility Cost For A Small Business? - Starter Story. [online] www.starterstory.com. Available at: https://www.starterstory.com/how-much-does-utility-costs-(office-space) [Accessed 22 Jan. 2023].
www.payscale.com. (2022a). Game Tester Salary in Germany ¦ PayScale. [online] Available at: https://www.payscale.com/research/DE/Job=Game_Tester/Salary [Accessed 21 Jan. 2023].
www.payscale.com. (2022b). Sound Designer Salary in Germany ¦ PayScale. [online] Available at: https://www.payscale.com/research/DE/Job=Sound_Designer/Salary [Accessed 21 Jan. 2023].
www.payscale.com. (2022c). Sound Engineer Hourly Pay in Germany ¦ PayScale. [online] Available at: https://www.payscale.com/research/DE/Job=Sound_Engineer/Hourly_Rate [Accessed 21 Jan. 2023].
www.payscale.com. (2022d). Video Game Programmer Salary in Germany ¦ PayScale. [online] Available at: https://www.payscale.com/research/DE/Job=Video_Game_Programmer/Salary [Accessed 21 Jan. 2023].
www.payscale.com. (2023a). Business Manager Salary in Germany ¦ PayScale. [online] Available at: https://www.payscale.com/research/DE/Job=Business_Manager/Salary [Accessed 22 Jan. 2023].
www.payscale.com. (2023b). Video Game Designer Salary in Germany ¦ PayScale. [online] Available at: https://www.payscale.com/research/DE/Job=Video_Game_Designer/Salary [Accessed 21 Jan. 2023].